## Sheet1
Task Order | RFS | Task | Functional_Role | Bravo_LCAT | Delta_LCAT | Hours | PoP | Expected Award Date
Delta | Delta RFS 005 | 1 | Agency Lead |  | Project Manager (Senior) 128C-3 | 2992 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Agency Lead |  | Project Manager (Senior) 128C-3 | 6611 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Automation Lead |  | Information Assurance/Security Specialist (Journeyman) 123C-2 | 5170 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Automation Lead |  | Information Assurance/Security Specialist (Senior) 123C-3 | 12690 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Capability Engineer |  | Hardware Engineer (Senior) 121C-3 | 496 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Capability Engineer |  | Hardware Engineer (Journeyman) 121C-2 | 3 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Capability Engineer |  | Hardware Engineer (Master) 121C-4 | 65 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Capability Engineer |  | Hardware Engineer (Senior) 121C-3 | 402 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Capability Engineer |  | Network Specialist (Senior) 126C-3 | 11280 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Chief Engineer |  | Enterprise Architect (Master) 114C-4 | 586 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Cyber Architect |  | Enterprise Architect (Master) 114C-4 | 564 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Delivery Manager |  | Project Manager (Senior) 128C-3 | 256 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Delivery Manager |  | Project Manager (Senior) 128C-3 | 1128 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Deputy PM |  | Project Manager (Senior) 128C-3 | 564 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | DI Engineer |  | Applications Developer (Journeyman) 102C-2 | 4857 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | DI Engineer |  | Applications Developer (Senior) 102C-3 | 19435 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Finance Manager |  | Financial Analyst (Journeyman) 117C-2 | 960 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Governance & Training Lead |  | Subject Matter Expert (Senior) 132C-3 | 376 | 36 | 2019-01-30
Delta | Delta RFS 005 | 4 | Governance & Training Lead |  | Subject Matter Expert (Senior) 132C-3 | 4230 | 36 | 2019-01-30
Delta | Delta RFS 005 | 4 | Governance & Training Lead |  | Subject Matter Expert (Journeyman) 132C-2 | 39000 | 36 | 2019-01-30
Delta | Delta RFS 005 | 2 | IA Engineer |  | Information Assurance/Security Specialist (Senior) 123C-3 | 7074 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Integration Lead |  | Subject Matter Expert (Senior) 132C-3 | 6930 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Integration Lead |  | Subject Matter Expert (Journeyman) 132C-2 | 1506 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Integration Lead |  | Subject Matter Expert (Master) 132C-4 | 4136 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Lab Manager |  | Network Specialist (Senior) 126C-3 | 376 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Lab Manager |  | Network Specialist (Journeyman) 126C-2 | 400 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Lead SIM |  | Enterprise Architect (Master) 114C-4 | 846 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | NAC Engineer |  | Network Specialist (Master) 126C-4 | 240 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | NAC Engineer |  | Network Specialist (Journeyman) 126C-2 | 11854 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | NAC Engineer |  | Network Specialist (Senior) 126C-3 | 34063 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Procurement Lead |  | Business Systems Analyst (Journeyman) 105C-2 | 192 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Procurement Lead |  | Business Systems Analyst (Journeyman) 105C-2 | 872 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Product Owner |  | Applications Systems Analyst (Senior) 103C-3 | 5835 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Project Coordinator |  | Business Process Consultant (Journeyman) 104C-2 | 128 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Project Coordinator |  | Business Process Consultant (Journeyman) 104C-2 | 6146 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Project Coordination Lead |  | Project Manager (Senior) 128C-3 | 1143 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Project Coordination Lead |  | Project Manager (Senior) 128C-3 | 6042 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Quality Lead |  | Quality Assurance Specialist (Journeyman) 129C-2 | 344 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Quality Lead |  | Quality Assurance Specialist (Journeyman) 129C-2 | 1175 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Requirements Analyst |  | Applications Systems Analyst (Journeyman) 103C-2 | 12251 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Requirements Analyst |  | Applications Systems Analyst (Entry Level) 103C-1 | 5644 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Requirements Lead |  | Applications Systems Analyst (Senior) 103C-3 | 5975 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | RFS Execution Lead |  | Project Manager (Senior) 128C-3 | 2695 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Program Manager |  | Program Manager (Master) 127C-4 | 256 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | RFS Execution Lead |  | Project Manager (Senior) 128C-3 | 2945 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Solution Architect |  | Subject Matter Expert (Senior) 132C-3 | 15839 | 36 | 2019-01-30
Delta | Delta RFS 005 | 1 | Solution Architecture Lead |  | Enterprise Architect (Master) 114C-4 | 256 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Solution Architecture Lead |  | Enterprise Architect (Master) 114C-4 | 4136 | 36 | 2019-01-30
Delta | Delta RFS 005 | 2 | Systems Test & Integration Engineer |  | Systems Engineer (Journeyman) 133C-2 | 4320 | 36 | 2019-01-30
Delta | Delta RFS 005 | 3 | Technical Writer |  | Technical Writer (Journeyman) 135C-2 | 14100 | 36 | 2019-01-30
Delta | Delta RFS 005 | 2 | Testing Lead |  | Test Engineer (Senior) 136C-3 | 6521 | 36 | 2019-01-30
Bravo | Bravo RFS 011 | 1 | Agency Lead | Project Manager (Senior) 128C-3 |  | 22 | 6 | 2019-12-19
Bravo | Bravo RFS 011 | 1 | PBS Support | Financial Analyst (Journeyman) 117C-2 |  | 22 | 6 | 2019-12-19
Bravo | Bravo RFS 011 | 1 | Project Expeditor | Administrative/Clerical (Joureneyman) 101C-2 |  | 109 | 6 | 2019-12-19
Bravo | Bravo RFS 011 | 1 | Quality Lead | Quality Assurance Specialist (Senior) 129C-3 |  | 8 | 6 | 2019-12-19
Bravo | Bravo RFS 011 | 1 | RFS Execution Lead | Project Manager (Senior) 128C-3 |  | 70 | 6 | 2019-12-19
Bravo | Bravo RFS 011 | 1 | Product Owner | Applications Systems Analyst (Journeyman) 103C-2 |  | 52 | 6 | 2019-12-19
Bravo | Bravo RFS 011 | 1 | RFS Portfolio Manager | Project Manager (Senior) 128C-3 |  | 13 | 6 | 2019-12-19
Bravo | Bravo RFS 011 | 4 | Training Specialist | Training Specialist (Senior) 137C-3 |  | 62 | 6 | 2019-12-19
Bravo | Bravo RFS 011 | 4 | Project Coordinator | Business Process Consultant (Journeyman) 104C-2 |  | 160 | 6 | 2019-12-19
Bravo | Bravo RFS 011 | 4 | DI Engineer | Applications Developer (Journeyman) 102C-2 |  | 252 | 6 | 2019-12-19
Bravo | Bravo RFS 013 | 1 | RFS Execution Lead | Project Manager (Senior) 128C-3 |  | 978 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 1 | Project Expeditor | Administrative/Clerical (Joureneyman) 101C-2 |  | 435 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 1 | Agency Lead | Project Manager (Senior) 128C-3 |  | 257 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 1 | PBS Support | Financial Analyst (Journeyman) 117C-2 |  | 217 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 1 | Quality Lead | Quality Assurance Specialist (Senior) 129C-3 |  | 113 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 1 | RFS Portfolio Manager | Project Manager (Senior) 128C-3 |  | 152 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 1 | Procurement Lead | Business Systems Analyst (Journeyman) 105C-2 |  | 65 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 1 | SDD Manager | Enterprise Architect (Master) 114C-4 |  | 8 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 1 | SIO Manager | Enterprise Architect (Master) 114C-4 |  | 8 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 1 | Product Owner | Applications Systems Analyst (Senior) 103C-3 |  | 120 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 2 | IA Engineer | Information Assurance/Security Specialist (Journeyman) 123C-2 |  | 40 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 2 | Systems Test & Integration Engineer | Test Engineer (Senior) 136C-3 |  | 320 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 2 | Requirements Analyst | Applications Systems Analyst (Entry Level) 103C-1 |  | 320 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 2 | Requirements Analyst | Applications Systems Analyst (Journeyman) 103C-2 |  | 320 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Endpoint Security Capability Lead | Network Specialist (Journeyman) 126C-2 |  | 3602 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Perimeter Defense Capability Lead | Network Specialist (Journeyman) 126C-2 |  | 9708 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Automation Lead | Information Assurance/Security Specialist (Senior) 123C-3 |  | 312 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Solution Architect | Subject Matter Expert (Senior) 132C-3 |  | 540 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Integration Lead | Subject Matter Expert (Senior) 132C-3 |  | 470 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Technical Writer | Technical Writer (Journeyman) 135C-2 |  | 312 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Project Coordinator | Business Process Consultant (Journeyman) 104C-2 |  | 740 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Requirements Analyst | Applications Systems Analyst (Journeyman) 103C-2 |  | 260 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Requirements Analyst | Applications Systems Analyst (Entry Level) 103C-1 |  | 940 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Training Specialist | Training Specialist (Senior) 137C-3 |  | 10 | 12 | 2019-01-20
Bravo | Bravo RFS 013 | 3 | Training Specialist | Training Specialist (Journeyman) 137C-2 |  | 40 | 12 | 2019-01-20
Bravo | Bravo RFS 012 | 1 | Agency Lead | Project Manager (Senior) 128C-3 |  | 16 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 1 | Quality Lead | Quality Assurance Specialist (Senior) 129C-3 |  | 26 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 1 | Project Expeditor | Administrative/Clerical (Joureneyman) 101C-2 |  | 44 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Capability Engineer | Subject Matter Expert (Senior) 132C-3 |  | 204 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Endpoint Security Capability Lead | Network Specialist (Journeyman) 126C-2 |  | 2512 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Endpoint Security Capability Lead | Network Specialist (Entry Level) 126C-1 |  | 942 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Endpoint Security Capability Lead | Network Specialist (Senior) 126C-3 |  | 942 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Technical Writer | Technical Writer (Journeyman) 135C-2 |  | 156 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Solution Architect | Subject Matter Expert (Senior) 132C-3 |  | 484 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Integration Lead | Subject Matter Expert (Senior) 132C-3 |  | 172 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Requirements Analyst | Applications Systems Analyst (Journeyman) 103C-2 |  | 243 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Requirements Analyst | Applications Systems Analyst (Entry Level) 103C-1 |  | 942 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Project Coordinator | Business Process Consultant (Journeyman) 104C-2 |  | 200 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Governance & Training Lead | Subject Matter Expert (Master) 132C-4 |  | 10 | 7 | 2019-01-03
Bravo | Bravo RFS 012 | 3 | Governance Analyst | Business Process Consultant (Journeyman) 104C-2 |  | 80 | 7 | 2019-01-03